## Section Title and team
Section | B-09
Title | Freelancing Portal
Team Lead | Sagar | S20160010075
| Aakash Shukla | S20160010001
Members | Pradeep Turan | S20160010064
| Ashish Kumar Patel | S20160020111
| Sarin Nikose | S20160010083
| Shubham Gupta | S20160010088

## Work Tracking
Project Level | 10th Oct to 2nd Nov |  |  | 2nd to 9th oct 2018 |  |  | 24 Sept to 1st oct 2018 |  |  | 24 Sept to 1st oct 2018 |  |  | 17 to 23rd Sept 2018 |  |  | 9 to 16 Sept 2018 |  |  | 1 to 9th Sept 2018
| Task Scheduled | Task Completed | Challenges | Task Scheduled | Task Completed | Challenges | Task Scheduled | Task Completed | Challenges | Task Scheduled | Task Completed | Challenges | Task Scheduled | Task Completed | Challenges | Tasks Scheduled | Tasks completed | Challenges | Tasks Scheduled | Tasks completed | Challenges
Feedback received on project | [9 empty] | MID SEM EXAM | [8 empty] | explore to store the database on local machine
Refactor Status
Team Work Breakdown Structure | [15 empty] | Login front-end, wireframe of the website
Aakash Shukla | Backend of browse jobs,filtering on the basis of skills and languages,including ajax in the browse jobs,common api integration,recommened jobs,profile of a user,edit profile,post project,usign cookies to post a project even without logging in,database hosting,login and authentiaction without api,signup and authentication without api | Backend of browse jobs,filtering on the basis of skills and languages,including ajax in the browse jobs,common api integration,recommened jobs,profile of a user,edit profile,post project,usign cookies to post a project even without logging in,database hosting,login and authentiaction without api,signup and authentication without api | Learned how ajax-django request and response works , integrating with common api for loggin in , msql linking and hosting. | Backend for post a project, post a task, project description and task description,Wire Frame Updation | Backend for post a project, post a task, project description and task description,Wire Frame Updation |  | Django model creation, and Activity Diagram Updation. | Django model creation, and Activity Diagram Updation. |  |  |  |  | Unit and system test case for Application and Selection | Unit and system test case for Application and Selection |  | review use case and report use case, Models | review and report use case
Sagar | Backend of my projects, project description, add task, task description,applicants applying for the task,selection of applicant as a contributor,task rating ,user rating,task submission,opening and closing of task and applying ajax to do it. | Backend of my projects, project description, add task, task description,applicants applying for the task,selection of applicant as a contributor,task rating ,user rating,task submission,opening and closing of task and applying ajax to do it. | Leared how to use ajax along with django and how to handle pages that would be visible to different types of user with differnt roles. Further linking the website through various points andmreducing the errors. | Backend for homepage,Dashboard, and process data design,Wire Frame Updation | Backend for homepage,Dashboard, and process data design,Wire Frame Updation |  | Backend for homepage, user authentication and use case diagram updation | Backend for homepage, user authentication and use case diagram updation |  |  |  |  | Unit and system testcase for Working on a Task and Ending a task | Unit and system testcase for Working on a Task and Ending a task |  | Search use case, Request use case, wireflow | Search and Request use case, wireflow for 3 webpages
Shubham Gupta | Backend for edit task, and update on frontend of task description, add and edit task, and browse jobs | frontend of <pages>,edit task frontend and backend for edit a task, sending data to the form and taking updation on it. |  | Front End for post project, post task, project description, ER diagram and Table updation, Wire Frame Updation | Front End for post project, post task, project description, ER diagram and Table updation, Wire Frame Updation |  | Backend for user authentication , Database Updation, Front End for homepage. | Backend for user authentication , Database Updation, Front End for homepage. |  |  |  |  | Unit and system testcase for Signup/Login and User rating | Unit and system testcase for Signup/Login and User rating |  | Use case for Login and WIshlist | Use case for login and user rating, wireflow for 3 webpages
Aashish Kumar Patel |  | black box testign of pages when they were being created manually,mantaing and updating the documents as the work was in progress,writing automated checking codes using selenium |  | Test Case Document and Class Diagram Updation,Wire Frame Updation,Frontend for add task and post project | Test Case Document and Class Diagram Updation,Wire Frame Updation,Frontend for add task and post project |  | Test Case Document, Model Creation and Frontend for homepage. | Test Case Document, Model Creation and Frontend for homepage. |  |  |  |  | Unit and system testcase for Close Project and Notification | Unit and system testcase for Close Project and Notification |  | Use case for close_project and notification | Use case for close_project and notification
Sarin Nikose | Backend of the rate user in the task description and also the rate task functionality, testing of login and sign up pages | black box testing of all the pages as they were being created manually,mantaining and updatingth document as the work was in progress, writing automated checking codes using selenium |  | Front End for Task Description,Test Case Document Completion and Detailed Design View, Wire Frame Updation | Front End for Task Description,Test Case Document Completion and Detailed Design View, Wire Frame Updation |  | Test Case Document and Detailed Design View | Test Case Document and Detailed Design View |  | MID SEM EXAM |  |  | Unit and system testcase for Post a project, post a task | Unit and system testcase for Post a project, post a task |  | Chat use case and login Front-end | Chat use case
Pradeep Turan | Making web pages responsive, and update on frontend of post a project, project description, applicants, and dashboard | frontend,making the webpages adjustable devices of all sizes |  | Front end for homepage, dashboard,project description, task description, ER diagram Updation, Wire Frame Updation | Front end for homepage, dashboard,project description, task description, ER diagram Updation, |  | Front end for login, signup, Database Updation | Front end for login, signup, Database Updation |  |  |  |  | Unit and system testcase for Verification of Task and task rating | Unit and system testcase for Verification of Task and task rating |  | Post ad and manage post use case | Post ad and manage post(system) use case